## Slide 1
Summary
Erwin Laure
KTH-PDC
(WP1)

## Slide 2: WP1
Add a deliverable outline together with contributing partners to the process (roughly 2.5 months before official due date)
The EB will review the revised due dates for the summer deliverables and milestones
Web site hosting remains an issue
In addition to PRACE and EGI outreach to relevant ESFRI projects (ELIXIR and INSTRUCT), and HEALTHGRID
Need to more closely monitor effort spenditure – PMB agreed to have monthly effort reports as of now.

## Slide 3: WP2
Events:
  Juelich event
  EGI Technical Forum – September in Lyon
  eScience conference – organize workshop
  HealthGrid conference in June (Birmingham)
Need to contact mapper
Link better into the existing communities (Dalton, Gromacs) – joint workshops etc.
  Organize a Gromacs/Dalton user group meeting
  Targeted workshops (based on user needs)
Get alpha-users involved in workshops

## Slide 4: Web Site
Be complementary to existing websites
Identify the main added value

## Slide 5: WP3
Better define feedback loop from WP4 to WP3
  Use ScalaLife channels first and if needed move to mailing lists of packages.
ScalaLife releases should be aligned with major releases if possible
Deadline for internal software releases should be aligned with all-hands meetings to allow for discussions and feedback
Provide easy-to-install versions for Grids and Clouds (VM images) – in collaboration with WP4
For future projects: work on visualization

## Slide 6: WP4
Start using project communication means (mailinglist and/or web)
Need pilot users for DALTON and DISCRETE
  Dalton is particularly important
  DISCRETE alpha-users will probably only come end of the year as it is new. Alpha-users will initially most likely not be large users.
ScalaLife will not become a resources provider to Alpha-Users
LRZ winterschool
Rethink how large validation runs we need really

## Slide 7: WP5
Direct messages towards targeted user groups
  Experienced, developing users
  Heavy users
  Experimentalists
Provide pre-packaged solutions for common problems
Need to be explicit on what effort we commit to in the calls in order not to overcommit
Who are the guinea pigs guiding the design of the competence center
What is the complementary to existing support structures

## Slide 8: WP5
What are the different kinds of experts available
  Deployment
  Applications
  Others?
Need a clear message
Do we need different processes for different targets?
Not integrate the community in the competence center, integrate the competence center in the community
Identify guinea pigs before going out to open call

## Slide 9: WP6
How to capture the knowledge of WP6?
  Start with existing walk-throughs
  Expose what possibilities are there
  Explain at what different aspects one could/should look at?

## Slide 10: WP7
Contacts between IRB and other partners (KTH, LRZ) need to be established.
How to involve the wider community in standardization work?
  Amber, Namd, …
  Link to ELIXIR and INSTRUCT?
Simulation portal, workflows
  be clear that this is a prototype, not building an infrastructure
  Needs to be integrated in a larger infrastructure eventually
Relate better to competence center
How to achieve impact on ELIXIR